## Sample Data
| WHAT IS CHANGING? ¦ IMPACTS |  | CHANGING FOR WHICH GROUPS? |  |  | TASKS PANEL |  |  |  |  | NOTES PANEL
# | Severity of Impact | Categorize / Summarize the Change | Organization (L1) | Organization (L2) | Organization (L3) | Task | Task Due Date | Assign Task to | Progress Status | Completion Date | Notes
1 | High | We are moving from a manual account provisioning process handled by the IT department for new user cloud accounts to an automated account provisioning tool. IT will no longer handle account setup, accounts will be generated from data HR enters into the employee master file. | Personnel Success | Human Resources | HR Group 1 | Interview Lead HR specialist for insights on any other impacts we haven't identified to their job role. | 2025-06-04 | John Doe | 100% | 2025-06-09 | We identified one more impact at the meeting to the onboarding process that has been added to the list of documentation updates.
2 | Mid | We are moving from a manual account provisioning process handled by the IT department for new user cloud accounts to an automated account provisioning tool. IT will no longer handle account setup, accounts will be generated from data HR enters into the employee master file. | Personnel Success | Human Resources | HR Group 2 | Review HR analyst job duties to see how they intersect with account provisioning task and gauge impact. | 2025-07-05 | Ashley Brown | 75% |  | A mid impact is estimated. There is one more document being reviewed.
3 | High | We are moving from a manual account provisioning process handled by the IT department for new user cloud accounts to an automated account provisioning tool. IT will no longer handle account setup, accounts will be generated from data HR enters into the employee master file. | Technology Success | Information Technology | Internal IT | Identify number of changes needed to the IT procedures manual, account provisioning chapter. | 2025-11-26 | Ashley Brown | 50%
4 | Low | We are moving from a manual account provisioning process handled by the IT department for new user cloud accounts to an automated account provisioning tool. IT will no longer handle account setup, accounts will be generated from data HR enters into the employee master file. | Corporate Success | Administration | Executive | Review procedure changes with Compliance Officer | 2026-06-18 |  | On Hold/Cancelled |  | This was deemed unnecessary because there are no procedural changes, just an update that improves compliance.
5 | High | We are bringing our marketing activities, which were previously outsourced, in-house by acquiring ABC Marketing Group and it will make up the company's new Marketing Department. Our current Marketing Liaison will be promoted to Marketing Director and oversee the new department. | Sales & Marketing | Marketing |  | Meet with Julie, who is being promoted to Marketing Director, to review potential external impacts. | 2026-12-22 | Ellen Doe | 25% |  | Awaiting a confirmation on meeting time availability.
6 | High | We are bringing our marketing activities, which were previously outsourced, in-house by acquiring ABC Marketing Group and it will make up the company's new Marketing Department. Our current Marketing Liaison will be promoted to Marketing Director and oversee the new department. | External Group | ABC Marketing |  | Review current impact assessment for the group being acquired. | 2026-12-14 | John Smith | 100% | 2024-07-06 | identified impacts have been noted and sent to the new Marketing Director for review.
7 | Low | We are bringing our marketing activities, which were previously outsourced, in-house by acquiring ABC Marketing Group and it will make up the company's new Marketing Department. Our current Marketing Liaison will be promoted to Marketing Director and oversee the new department. | Finance | Accounting | Payroll & Benefits | Review impact assessment with accounting team to confirm "low" is the correct impact level. | 2026-12-27 | John Smith | Assigned (Not Started)
8 | High | We are moving away from a hierarchy culture (slow to innovate) to an adhocracy culture adopting and promoting a new "Innovation Always" initiative, where input and ideas are welcome, and innovation will be part of the company mission. | Corporate Success | Administration | Executive | Meet with project lead and project sponsor to get a full understanding of organizational changes happening per each organizational group | 2027-01-22 | Jill Doe | 50% |  | Have met with project lead, will be meeting with project sponsor on 8/4 and will enter organizational groups into template after that.
9 | High | All video meetings and webinars are going to be done in MS Teams instead of Go-to-Meeting, as the company is already using Teams for internal communications. This will lower overall SaaS costs by $3840/year. | Sales & Marketing | Product Education | Digital | Request the current state and future state process flows for webinar presentations. | 2027-02-11 | Akosh Doe | 100% | 2024-08-24 | The process flows for this function have been added to the Change Team's SharePoint folder.
10 | Mid | All video meetings and webinars are going to be done in MS Teams instead of Go-to-Meeting, as the company is already using Teams for internal communications. This will lower overall SaaS costs by $3840/year. | Sales & Marketing | Sales | Sales Team |  | 2027-06-18
11 | Low | All video meetings and webinars are going to be done in MS Teams instead of Go-to-Meeting, as the company is already using Teams for internal communications. This will lower overall SaaS costs by $3840/year. | Sales & Marketing | Sales | Sales Team | Review initial change impact assessment with manager overseeing department and job function. | 2027-09-12 | Shawna Smith | Assigned (Not Started)
Change Impact Assessment with Sample Data (Comprehensive Template)
for Conducting Impacts to Processes, Systems, and People
Note on C3: Admin: What is the severity of impact (Low, Mid, High, No Impact, or TBD)
Note on D3: O A: WHAT TO ENTER IN THIS FIELD It is recommended that you categorize the change on each row for easy reference and grouping with other rows. But you can also leave this blank. Each row in a Change Impact Assessment template includes details on something that is changing. In some cases that change will be related to other changes entered in other rows within this document. Naming each row on this template allows you / your team to easily categorize each row, and to easily identify and filter for rows with changes that are related. Examples of how you can name your rows: - Accounting Process Change - Organizational Culture Change - Critical Data Restructuring and New Job Skills - Salesforce Account Opening Process - Marketing Group Restructuring

## OCM Change Assessment Template
| WHAT IS CHANGING? ¦ IMPACTS |  | CHANGING FOR WHICH GROUPS? |  |  | TASKS PANEL |  |  |  |  | NOTES PANEL
# | Severity of Impact | Categorize / Summarize the Change | Organization (L1) | Organization (L2) | Organization (L3) | Task | Task Due Date | Assign Task to | Progress Status | Completion Date | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
Change Impact Assessment (Comprehensive Template)
for Conducting Impacts to Processes, Systems, and People
Note on C3: Admin: What is the severity of impact (Low, Mid, High, No Impact, or TBD)
Note on D3: O A: WHAT TO ENTER IN THIS FIELD It is recommended that you categorize the change on each row for easy reference and grouping with other rows. But you can also leave this blank. Each row in a Change Impact Assessment template includes details on something that is changing. In some cases that change will be related to other changes entered in other rows within this document. Naming each row on this template allows you / your team to easily categorize each row, and to easily identify and filter for rows with changes that are related. Examples of how you can name your rows: - Accounting Process Change - Organizational Culture Change - Critical Data Restructuring and New Job Skills - Salesforce Account Opening Process - Marketing Group Restructuring

## Dropdowns (hidden)
Low
Mid
High
No Impact